Meeting minutes made by Teagan Reddy (SU no. 26012243)

Date: 11/03/2026

Agenda:

- Clarify a few issues regarding my project proposal such as end-of-life requirements, budget and components

- Clarify the project proposal Gantt Chart

- Clarify the capital costs for budget planning

Summary:

- Reviewed the concerns about my project proposal

- Recycling methods for the end-of-life strategy but be specific to the parts being discarded

- Regarding software licenses for budget planning, just state that the educational license will be used through the university

- Regarding the budget and planning in the project proposal, do not assume there is access to any previous components

- Review Gantt Chart in Microsoft Excel against Microsoft Projects

- Capital costs refer to purchased items that do not run out after use, and costs more than R2000

- Confirm if budget has been updated from R5000 to R7000 by next week (18 March)

- Project proposal due on 13 March

Signed by supervisor: